## Slide 1
PROJECT BRIEF · MAIN BRANCH
EconoCausal
What is built today, what comes next, and how the dashboard shows it
Five slides. Two of them are forward-looking: the predicted work left on main, and the dashboard flow used to show the result. No causal number is claimed anywhere in this deck.
REPOSITORY
snigdhasudheer/Infotact_project1
REVIEWED
27 Oct 2026 · main @ b01a204
IN THIS BRIEF
01 Today: built vs outstanding
02 Predicted further work
03 Dashboard: how it shows results
04 What the demo can claim
41 commits
18 merged PRs
16 unit tests
5 API routes
2/12 requirements done
Evidence read from the repository, not from its roadmap.
Notes: Five slides, two of them forward-looking. Everything factual here was counted from the main branch - 41 commits, 18 merged PRs, 16 tests, five API routes, and 2 of 12 requirements genuinely complete. The second half of the brief is a prediction, and it is labelled as one.

## Slide 2
01 · TODAY
Built vs outstanding, on one screen
Two of twelve requirements are complete, four are partial. Nothing downstream of the export estimates an effect.
41
commits on main
GitHub history
18
merged PRs · 0 open
all merged into main
16
unit tests · no CI
data utilities only
5
API routes
upload · export · report
ON MAIN
DELIVERED
Dataset decision
Retail vs Hillstrom compared and documented
Cleaning & validation
8 required columns, 5 tests, 400 on bad input
Product-month export
6-column CSV, 2-dp rounding, 7 tests
FastAPI + React shell
upload → validate → export → report, wired
Methodology notes
8 identification assumptions, limits stated
OUTSTANDING
STILL OPEN
Treatment, outcome, covariates
blocks everything below
Causal DAG
no graph, no defensible estimator
DML estimate with intervals
EconML not installed
DoWhy refutation
no placebo or sensitivity checks
Budget optimisation
needs a validated estimate
Dashboard placeholders
4 of 6 panels still empty
Read it this way: the data and delivery layer is credible and tested; the four requirements that give the project its name are untouched.
EconoCausal · project brief · main branch
02
Notes: Keep this to one breath. Left column is what a reviewer can click today; right column is what is missing. The important nuance is at the bottom: the first item on the right - the treatment, outcome and covariate definitions - belongs to Section A, which is why the causal track has not started.

## Slide 3
02 · PREDICTED
What comes next, week by week
Four predicted weeks built from the effort each task actually needs. Confidence reflects how much is outside Section B's control.
WEEK 1
Unblock
C1
Section A definitions signed off
P3
Duplicate id + port mismatch fixed
P5–P6
Untrack .pyc, add CI workflow
Predicted: DAG committed, CSV loads in the dashboard, CI green
WEEK 2
Estimate
C2
Analysis table build script + graph
C3
LinearDML, cross-fit, cluster-robust CI
P2A
Causal Analysis card fed by real output
Predicted: first ATE with a confidence interval on screen
WEEK 3
Validate
C4
Placebo, random cause, subset refutations
P2B
Overlap + heterogeneity charts
P1
Product-month CSV into EDA section
Predicted: estimate survives refutation, or gets re-scoped
WEEK 4
Decide
C5
SciPy allocation, labelled simulated
P4
Fetch script or fixtures for reproducibility
—
Final report + demo run-through
Predicted: one quantified recommendation plus its caveat
The prediction that matters: by week 4 the dashboard's empty ATE card holds a number with a confidence interval, or the project honestly ships a Hillstrom e-mail-uplift result instead. Both are defensible; a filled card with no identification argument is not.
Confidence: high · medium · low
Effort: C1 2–3 days · C2 1 wk · C3 1 wk · C4 3–4 days · C5 4–5 days
EconoCausal · project brief · main branch
03
Notes: This is the forward-looking slide. Four weeks, not four months: the work left is bounded, and the only real risk sits in week 1. Point at the confidence pills - everything Section B controls is high, everything depending on Section A or on whether price variation exists is medium or low. The bottom strip is the commitment: a number with an interval, or an honest re-scope.

## Slide 4
03 · DASHBOARD
How the dashboard is used to show results
Six panels, one story: upload → describe → estimate → recommend → allocate. Each panel names its own data source.
PANEL
WHAT IT SHOWS
WHERE THE DATA COMES FROM
STATE NOW → AFTER THE PREDICTED WORK
Dataset & EDA
Validation summary, 5-row preview, quality tiles
/api/upload → pandas
live, one file at a time → adds missing-value and month tiles
Product-month charts
Price vs quantity by month, per product
product_month_summary.csv
component exists, no data → real Plotly trend per product
Causal Analysis
ATE, 95% CI, sample size, overlap diagnostics
DML output (JSON)
four “Pending” cards → estimate + interval + diagnostics
Recommendations
Products and segments ranked by estimated effect
ATE + heterogeneity
placeholder → ranked table with effect sizes
Budget Optimization
Allocation vs baseline, explicitly simulated
SciPy scenario
placeholder → labelled simulation, never a promise
THE FIVE-MINUTE DEMO FLOW
1
Upload sample_upload.xlsx
validation + summary appears
2
Export the product-month CSV
the hand-off table downloads
3
Open Dataset & EDA
one real trend chart, real numbers
4
Open Causal Analysis
ATE, interval, overlap — or say why not
5
Open Budget Optimization
scenario, labelled simulated
Never show a placeholder: hide an unfinished panel or label it “in progress”. A reviewer reads “Pending” as unfinished scaffolding, which costs more than an empty tab.
EconoCausal · project brief · main branch
04
Notes: This is the showing strategy. Each row says what a panel will display and which file or endpoint feeds it - that is the credibility test. The flow at the bottom is the demo order: upload, export, describe, estimate, allocate. Five minutes, no placeholder cards on screen. If step 4 is not ready, say so out loud rather than showing a blank card.

## Slide 5
04 · WHAT THE DEMO CAN CLAIM
A defensible pitch, and its limits
CAN CLAIM
A validated, tested pipeline on real retail data
Descriptive price–demand evidence, clearly labelled as association
A DML estimate with a confidence interval and refutation checks, once C3–C4 land
A simulated allocation showing how budget would move
CANNOT CLAIM
A causal discount effect from historical retail prices
ROI or savings produced by the optimiser
That an e-mail uplift equals a price elasticity
NEXT SEVEN DAYS
1
Get Section A definitions in writing
PROJECT LEAD
2
Ship the unblocked fixes: P1, P3, P5, P6
SECTION B
3
Build the analysis table and commit the DAG
SECTION B
ONE DECISION, TODAY
Do we estimate the e-mail uplift Hillstrom can support, or hold for a pricing design we do not have yet?
It decides whether week 4 ships a number or a caveat.
Sources: snigdhasudheer/Infotact_project1 @ main · README, docs/day2, docs/day5, requirements-checklist, main.py, frontend/src, test suite
EconoCausal · project brief · main branch
05
Notes: Close on the boundary, not a summary. Left: what this project can stand behind today and after week 4. Right: the three claims that would break under questioning - the discount effect, the optimiser's savings, and relabelling an e-mail uplift as price elasticity. Then ask for the one decision that determines whether week 4 produces a number or a caveat.