## Slide 1
PROJECT STATUS REVIEW · MAIN BRANCH
EconoCausal
Causal dynamic pricing via Double Machine Learning
Where the project actually stands: what is built on main, what is still open, and what it takes to close the gap — evidence taken from the repository, not from the roadmap.
REPOSITORY
snigdhasudheer/Infotact_project1
REVIEWED
27 October 2026 · main @ b01a204
PROGRAM
Infotact Project 1 · Section B delivery
41 commits
18 merged PRs
0 open PRs
16 unit tests
5 API routes
Notes: Open by naming the source: the main branch of snigdhasudheer/Infotact_project1, reviewed today (commit b01a204). Say up front that every number in this deck was counted from the repository, because the repository's own roadmap and requirements checklist are out of date.

## Slide 2
CONTENTS
What this deck answers
Four questions, in the order a reviewer would ask them.
01
Where the project stands
Commits, pull requests and a measured read of the 12-point requirements checklist.
02
What has been delivered
Data validation, product-month export, FastAPI endpoints, React dashboard and the test suite.
03
What is still missing
Treatment definition, causal DAG, DML estimates, refutation, budget optimizer and the final report.
04
How to close the gap
A sequenced four-phase plan with gates, owners, risks and the one open decision.
Scope: only the main branch of snigdhasudheer/Infotact_project1, as reviewed on 27 October 2026. No projected results appear in this deck.
EconoCausal · Project status review · main branch
02
Notes: Four questions. Set the expectation that the last two are the useful ones: what is missing, and what closes it.

## Slide 3
ORIENTATION
The project at a glance
A causal-inference study of pricing and marketing, delivered as a documented analysis plus a dashboard.
OBJECTIVE
Estimate how a pricing or marketing intervention changes customer behaviour, then spend a limited promotional budget using those estimates rather than intuition. Online Retail and Hillstrom were both assessed as candidate datasets.
SECTION A
Problem definition
Treatment, outcome, covariates, causal DAG, identification assumptions
SECTION B
Methodology & delivery
Documentation, validation utilities, API, dashboard, reporting
STACK
IN USE ON MAIN
Python · pandas · openpyxl
FastAPI · Uvicorn
React 19 · Vite
Plotly.js · react-plotly
PLANNED, NOT INSTALLED
EconML (Double ML)
DoWhy (refutation)
SciPy (optimizer)
scikit-learn (nuisance models)
DELIVERY SO FAR
Day 1
Dataset overview
Day 2
Decision + schema
Day 3
Hillstrom QA
Day 4
Dashboard shell
Day 5
Methodology
Day 6
Export + validator
EconoCausal · Project status review · main branch
03
Notes: One-line framing: this is a causal-inference study delivered as documentation plus a dashboard. Note the two workstreams - Section A owns the definitions, Section B owns the methodology and delivery - because that split explains why the causal track is idle.

## Slide 4
EVIDENCE
Where main stands today
Counted directly from the repository, not from the roadmap in the codebase.
41
commits on main
18 merged pull requests · 0 open
18
merged PRs
every PR since Day 1 merged cleanly
16
unit tests
Python utilities only · no CI workflow
5
API routes
health, upload, export, report, root
REQUIREMENTS CHECKLIST, RE-SCORED
33 %
2 of 12 requirements complete, 4 partially delivered
Complete
Partial
Not started
Ticks are this review's assessment; docs/requirements-checklist.md still shows 0/12 and calls the backend “pending”, which main has already overtaken.
3 contributors
5 notebooks
3 docs
5.9 k lines JSX
0 CI workflows
EconoCausal · Project status review · main branch
04
Notes: Hard evidence only. 41 commits, 18 merged PRs, none open, 16 unit tests, 5 API routes. Then the re-score: 2 of 12 requirements complete and 4 partial, which is 33 percent. The committed checklist still says 0/12 and 'backend pending' - main has overtaken it.

## Slide 5
DELIVERED
Six milestones already on main
Each card is backed by merged pull requests and files in the repository.
DAY 1–2
Dataset decision & schema
Online Retail and Hillstrom compared, schemas documented, and the causal limits of each written down.
#1 – #4
DAY 2–3
Cleaning & upload validation
Eight required columns enforced; duplicates, missing values and non-positive values handled. 5 tests.
#3, #9
DAY 3–4
Hillstrom quality & treatment
Missing values, duplicate profiles and the three marketing segments profiled before any modelling.
#5, #6
DAY 4
Dashboard shell & navigation
React + Plotly layout with a working sidebar, GitHub commit feed and merged-PR panel.
#7, #11
DAY 5
Methodology & assumptions
Eight identification assumptions documented, plus the exact limits of observational price data.
#10
DAY 6
Export, validator & report
Product-month CSV export, six-column CSV validator with 7 tests, and a downloadable dataset report.
#12 – #18
All 18 pull requests were merged into main; nothing is sitting open or unreviewed.
EconoCausal · Project status review · main branch
05
Notes: Six milestones, each traceable to a PR range. Keep this brief; it is the 'credit where due' slide.

## Slide 6
DELIVERED · DATA LAYER
The data foundation is solid
Two datasets inspected and documented — with the caveats that decide what can be estimated later.
PRIMARY
Online Retail · UCI
541,909 rows × 8 columns → 524,878 rows × 9 columns after cleaning
Exact duplicate rows removed
5,268
Missing Description
1,454
Missing CustomerID (kept)
135,080
UnitPrice ≤ 0 / Quantity ≤ 0
2,517 / 10,624
Revenue = Quantity × UnitPrice added as the analysis feature.
SECONDARY
Hillstrom · e-mail test
64,000 rows × 12 columns · 0 missing values
Randomised arms
Mens / Womens / No e-mail
Outcomes
visit, conversion, spend
Duplicate rows flagged
6,562 (not removed)
Treatment type
e-mail, not price
Only randomised arm in either dataset.
Why two datasets — No shared column or join key exists, so they stay separate; merging them was explicitly rejected in Day 2.
Open item — Hillstrom's 6,562 duplicate profiles were flagged but not investigated — removing them now would change the estimand.
HAND-OFF SCHEMA · PRODUCT_MONTH_SUMMARY.CSV
StockCode · Month · Average_Price · Total_Quantity · Total_Revenue · Transaction_Count
Six columns, validated before the dashboard consumes them. This is the table the causal stage must build on.
EconoCausal · Project status review · main branch
06
Notes: Online Retail: 541,909 rows down to 524,878 after cleaning, with the four quality counts on screen. Hillstrom: 64,000 rows, zero missing, but 6,562 duplicate profiles flagged and not investigated. Neither dataset can be joined to the other, so the merger was rejected deliberately.

## Slide 7
DELIVERED · APPLICATION LAYER
What actually runs end to end
A working upload → validate → export → report pipeline, wrapped in a React dashboard.
FASTAPI · MAIN.PY
GET
/api/health
Liveness probe for the dashboard
POST
/api/upload
.xlsx validation, 5-row preview, summary
POST
/api/export-product-month
Product-month CSV, 6 columns, 2-dp rounding
POST
/api/dataset-report
Plain-text data-quality report
GET
/
Service banner
Type check on every route; bad input returns 400, never a silent 200.
REACT DASHBOARD · VITE
Sidebar navigation
6 sections wired to smooth scroll
Upload panel
Drag-drop .xlsx, preview table, summary tiles
Export + report
Downloads CSV and .txt from the API
GitHub activity
Live commits and merged PRs from main
Plotly EDA charts
Component built, waiting on data
Recommendations, budget
Placeholders only
Read this as a pipeline, not a model. Upload, validation, export and reporting are production-shaped and tested. Nothing downstream of the export estimates a causal effect yet.
EconoCausal · Project status review · main branch
07
Notes: Walk the four routes left to right, then flag that the frontend is a real pipeline: upload, validate, export, report. The Plotly EDA component exists but is rendered without data, and Recommendations and Budget are still placeholders.

## Slide 8
DELIVERED · QUALITY
16 tests, no CI, no API coverage
Real automated coverage of the data utilities — with a gap where the web layer sits.
TEST SUITE · PYTHON -M UNITTEST
test_validate_upload.py
5
test_export_product_month.py
4
test_validate_product_month_csv.py
7
16 tests pass on synthetic fixtures — no real dataset is shipped
COVERED
· Required vs unexpected columns rejected
· Empty files, blank codes, bad YYYY-MM values
· Negative prices, quantities and revenue
· Non-integer transaction counts
· Duplicate StockCode + Month keys
· Non-zero exit code on failure
No API tests
The five FastAPI routes have no request-level tests at all.
No frontend tests
oxlint is configured, but no component or interaction test exists.
No CI
No .github/workflows — the 16 tests only run when a developer remembers.
No pinned deps
requirements.txt omits EconML, DoWhy, SciPy and scikit-learn.
EconoCausal · Project status review · main branch
08
Notes: 16 tests is real coverage of the data utilities - column checks, empty files, bad months, negative values, duplicates, exit codes. The gaps are structural: no API tests, no frontend tests, no CI, and requirements.txt has none of the causal libraries.

## Slide 9
THE HONEST GAP
Why the centrepiece result is still missing
01
Online Retail has no randomised price
Prices are historical and set by the retailer. Without a treatment assignment, a price–quantity relationship cannot be read as a causal effect.
02
Hillstrom randomises e-mail, not price
It can support a defensible e-mail uplift estimate. That is a different estimand from discount elasticity and must not be relabelled as one.
03
No treatment, outcome or covariate set is signed off
Section A still owns those definitions. Until they arrive there is no DAG, no valid estimator and no defensible budget optimisation.
CONSEQUENCE
The dashboard is deliberately right to show “Not yet estimated”.
Filling those cards with numbers before the identification argument exists would be the single most damaging thing this project could do — it is the first thing a reviewer will test.
Unblocked by: Section A definitions + a documented identification strategy
Everything on the next three slides depends on resolving 01 – 03.
EconoCausal · Project status review · main branch
09
Notes: The pivotal slide. Three reasons the headline result is missing: no randomised price in Online Retail, Hillstrom randomises e-mail not price, and Section A has not signed off treatment, outcome, or covariates. The dashboard showing 'Not yet estimated' is correct behaviour, not a defect.

## Slide 10
REMAINING WORK · SCORECARD
Twelve requirements, re-scored against main
The checklist flags itself as out of date; this is what the code supports today.
01 Select and document the dataset
Complete
02 Validate and clean the data
Complete
03 Exploratory data analysis
Partial
04 Define treatment, outcome, covariates
Not started
05 Create a causal DAG
Not started
06 Implement DML with EconML
Not started
07 Validate assumptions with DoWhy
Not started
08 Optimise budget with SciPy
Not started
09 FastAPI backend endpoints
Partial
10 React dashboard with Plotly
Partial
11 Tests and reproducibility
Partial
12 Final report and project demo
Not started
Bottom line: the project has built a credible data and delivery layer. The four requirements that give it its name — DAG, DML, refutation, optimisation — are all still untouched.
EconoCausal · Project status review · main branch
10
Notes: The re-scored checklist, requirement by requirement. Land the bottom line: the four requirements that give the project its name - DAG, DML, refutation, optimisation - are all untouched.

## Slide 11
REMAINING WORK · TRACK 1
Causal core — five tasks, strictly ordered
Each task is a gate: the next one cannot start honestly until the previous one is signed off.
C1
Freeze Section A definitions
Treatment, outcome, covariates, estimand and unit of analysis, written into docs/.
EFFORT
2–3 days
DEPENDS ON
Blocker for C2 – C5
Done when: Signed definitions doc
C2
Build the analysis table and DAG
Product-month or customer-level panel, plus a committed DAG (dagitty / DoWhy graph).
EFFORT
1 week
DEPENDS ON
Needs C1
Done when: Reproducible build script + DAG
C3
Estimate with EconML DML
LinearDML or CausalForestDML, cross-fitting, cluster-robust intervals, overlap checks.
EFFORT
1 week
DEPENDS ON
Needs C1, C2
Done when: ATE + CI + overlap report
C4
Refute with DoWhy
Placebo treatment, random common cause, data subset and sensitivity analysis.
EFFORT
3–4 days
DEPENDS ON
Needs C3
Done when: Refutation table in the report
C5
Allocate budget with SciPy
Optimise spend from estimated responses; label every output as a simulation.
EFFORT
4–5 days
DEPENDS ON
Needs C3, C4
Done when: Scenario + stated assumptions
Sizing: C1 is days, not weeks — but it belongs to Section A and is the reason this track has not started. C3 and C4 are the two tasks that turn this from a data dashboard into a causal study; budget roughly one week each with a clean analysis table.
EconoCausal · Project status review · main branch
11
Notes: Causal track: five tasks in strict order, with effort and the gate for each. C1 is the blocker and it belongs to Section A. C3 and C4 are where this becomes a causal study.

## Slide 12
REMAINING WORK · TRACK 2
Product and platform — six fixes, none blocked
This track can start today while Section A finishes its definitions.
P1
Wire product-month CSV end to end
Export and validator exist, but the dashboard never loads product_month_summary.csv.
Unblocked
P2
Replace dashboard placeholders
Four panels still say “will appear here”. Needs real EDA charts and the ATE cards.
Unblocked
P3
Fix wiring defects
Duplicate section id, report endpoint on port 8001 while the rest use 8000, EDACharts rendered without props.
Unblocked
P4
Restore reproducibility
data/ is git-ignored, so notebooks cannot run from a fresh clone. Add a fetch script or sample fixtures.
Unblocked
P5
Repository hygiene
Two .pyc files are tracked, and README.md holds Day-6 notes instead of a project overview.
Unblocked
P6
Add CI
GitHub Actions running the 16 tests plus oxlint on every pull request.
Unblocked
EconoCausal · Project status review · main branch
12
Notes: Platform track: six fixes, none blocked, start today. P1 and P3 are the two that most affect what a reviewer sees, because wiring the CSV and removing the duplicate section id are small but visible.

## Slide 13
PLAN
Four phases to a defensible result
Sequenced so that visible progress never outruns the identification argument.
PHASE 0
Unblock
Week 1
· C1 definitions signed off
· P3 defects fixed
· P4–P5 hygiene
Gate: DAG + data contract agreed
PHASE 1
Estimate
Weeks 1–2
· C2 analysis table + DAG
· C3 DML with intervals
· C4 refutation
Gate: ATE with CI survives refutation
PHASE 2
Surface
Weeks 2–3
· P1 CSV into dashboard
· P2 real charts + ATE cards
· P6 CI green
Gate: no placeholder panels left
PHASE 3
Decide
Weeks 3–4
· C5 SciPy allocation
· Recommendations
· Report + demo
Gate: simulated allocation, labelled
If Section A slips: run Phase 0 and Phase 2 in parallel and hold the causal slides empty. A dashboard with honest blanks is recoverable; a dashboard with invented elasticities is not.
EconoCausal · Project status review · main branch
13
Notes: Four phases with gates. The point of the sequence is that nobody builds an optimiser on top of an unvalidated estimate. If Section A slips, run Phase 0 and Phase 2 in parallel and keep the causal slides empty.

## Slide 14
RISKS
Four things that could sink this
Each has an owner-facing mitigation, not just a warning.
RISK
WHY IT MATTERS
MITIGATION
Section A definitions never land
The entire causal track stays at zero and the deck repeats itself next week.
Set a hard date; escalate to the project lead; ship P1–P6 meanwhile.
No valid price variation in the data
A DML price elasticity would be an artefact of confounding, not a causal number.
Re-scope to Hillstrom e-mail uplift, or state a simulated-price design explicitly.
Placeholders still visible at demo
Reviewer sees “Pending” cards and reads the project as unfinished scaffolding.
Hide unfinished sections behind a “in progress” tab until real output exists.
Nothing is reproducible from the clone
data/ is ignored, .pyc files are tracked, no CI: results cannot be re-run.
Fetch script or fixtures, untrack build artefacts, add Actions workflow.
EconoCausal · Project status review · main branch
14
Notes: Four risks, each with a mitigation someone owns. The second is the technical one: without valid price variation, any DML elasticity is a confounded artefact.

## Slide 15
NEXT SEVEN DAYS
What needs to happen
1
Get the Section A definitions in writing
Treatment, outcome, covariates, estimand. This unlocks everything else.
PROJECT LEAD
2
Choose the causal target
Hillstrom e-mail uplift (identifiable now) or retail price elasticity (needs a design).
SECTION A + B
3
Ship the unblocked platform fixes
P1, P3, P5, P6 — CSV into the dashboard, defects, hygiene, CI.
SECTION B
4
Stand up the analysis table and DAG
Reproducible build script plus a committed graph.
SECTION B
5
Then, and only then, train DML
One estimator, cluster-robust CIs, overlap diagnostics, refutation table.
SECTION B
Open decision for the reviewer: do we estimate the e-mail uplift that Hillstrom can actually support, or hold for a pricing design we do not yet have? The answer determines whether the next milestone produces a number or a caveat.
Sources: snigdhasudheer/Infotact_project1 @ main · README, docs/day2, docs/day5, docs/requirements-checklist, main.py, frontend/src, test suite
Notes: Close on the decision, not a summary. Ask the reviewer: Hillstrom e-mail uplift that the data can actually identify, or wait for a pricing design we do not have? The answer decides whether the next milestone ships a number or a caveat.